## Front page
Surcotec
ST-F-09-01-8111 - Rev1 - Atlantis Foundries - 160Ø Linear Shafts for HVOF Coating
Revision:1
Cover Page
Job Number
IOB 22941
Part Description
160 Ø Linear Shafts for HVOF Coating
Number of parts : | 2-off
Responsible person : | Sheldon Deysel
Customer : | Atlantis Foundries
Customer job number: | N/A
Customer ref. number: | N/A
Quote number: | SCT - 7725
Surcotec Ref. Number: | 26-01-027
Customer order number:
Customer Drawing number(s) : | N/A
Date created: | 20.01.2026
Due date: | 10-15 Working Days
Delivery note(s):
NOTE(S)
ISO 9001:2015
Surcotec Confidential

## Quality control plan
Surcotec
ST-F-09-01-8111 - Rev1 - Atlantis Foundries - 160Ø Linear Shafts for HVOF Coating
Revision:1
Quality controll plan
Purpose: Prepared by responsible engineer to describe the actual work to be done. Defines customer QC requirements.
Job number: | IOB 22941 |  | Description: | 160 Ø Linear Shafts for HVOF Coating |  | QC Clearance |  |  |  | Total time | Comments
Revision: | 2-off |  | Quantity: | 2-off |  | Surcotec |  | Subcontractor
Operation |  | Description |  |  |  | Name | Date | Name | Date
Register job and Issue WDP document |  | Register job
Incoming inspection |  | Visual, dimensional & geometrical inspection. Record all pertinent dimensions, tolerences & sizes. Please take photos of all damage for record keeping before NDT & machining Create drawing/sketch if none was provided by client. Record all findings on pre-inspection report & submit to (BG)
Pre-machining |  | Set-up stock material in the lathe. Rouch machine the shaft to 5mm -7mm from final size. Shaft to be sent for stress relief afterwards Ensure radii in all corners. Complete all required paperwork & sign.
NDT |  | Dye penetrant test Rudder shafts with water washable Ardrox 907PB dye penetrant Allow to stand for 30 mins minimum and wipe all excess dye with soft paper towel or cloth Apply Ardrox 9D1B developer. Any relevant indications to be reported to Supervisor immediately before removing developer from hydraulic rod
Pre-machining |  | Set-up Shaft in the lathe. Clock the main body front, middle and back end to check if Rudder shafts bent. TIR<0.015mm (TIR include all journals and roll bodies if applicable) Pre-machine the indicated area on main body to remove damage and / or old coating ,Pre-machine size must be minimum 0.5mm under final size.Operator to clean part with acetone after pre-machining Ensure radii in all corners. Complete all required paperwork & sign.
In Process Inspection |  | Artisan to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
NDT |  | Dye penetrant test Rudder Shafts main body with water washable Ardrox 907PB dye penetrant Allow to stand for 30 mins minimum and wipe all excess dye with soft paper towel or cloth Apply Ardrox 9D1B developer. Any relevant indications to be reported to Supervisor immediately before removing developer from hydraulic rod
Preperation for pre heating and sand blast ( Intermediate Build up) |  | Pre-heat part. Wash with acetone and repeat process until no indication of contimaminents visible.
Gritblasting ( Intermediate Build Up ) |  | Grit blast using GH18/25 Chilled Iron grit. Gritblasting to be done until the area to be coated exhibits a uniform structure to Sa2½ standard. After gritblasting clean dust by blasting with clean dry compressed air, and check for trapped grit and residue.
In Process Inspection |  | QC Specialist, Forman or Superintendant to perform in process checking for blasting profile using the Elcometer and record all findings. | [8 empty] | HOLDING POINT
Masking for coating ( Intermediate Build Up ) |  | Use specialised tape or anti bond paint to mask non-spray areas.
Thermal spray Intermediate Coating |  | Spray 1.2mm oversize on diameter on pre-machined area. Use 1302(10T)wire to do build up. Complete and sign all relevant paperwork
In Process Inspection |  | Spray Technician to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
Pre-machining Intermediate Build Up |  | Set-up in the lathe. Clock to the Pre Machine References, TIR<0.015mm (TIR include all journals and roll bodies if applicable) Pre-machine the Sprayed Journal 0.4mm under final size in preperation for HVOF Coating Ensure radii in all corners and no shatter or spiral Complete all required paperwork & sign.
In Process Inspection |  | Artisan to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
Preperation for pre heating and sand blast for HVOF Coating |  | Pre-heat part. Wash with acetone and repeat process until no indication of contimaminents visible.
Gritblasting for HVOF Coating |  | Grit blast using GH18/25 Chilled Iron grit. Gritblasting to be done until the area to be coated exhibits a uniform structure to Sa2½ standard. After gritblasting clean dust by blasting with clean dry compressed air, and check for trapped grit and residue.
In Process Inspection |  | QC Specialist, Forman or Superintendant to perform in process checking for blasting profile using the Elcometer and record all findings. | [8 empty] | HOLDING POINT
Masking for HVOF coating |  | Use specialised tape or anti bond paint to mask non-spray areas.
HVOF spray topcoat |  | Spray 3801(CRC 425) top-coat on pre-machined area on main body Spray 0.4mm oversize on diameter for grinding/machining allowance. Complete all required paperwork & sign.
In Process Inspection |  | Spray Technician to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
Final-grinding |  | Set Up on Toss Grinder, Clock to pre-machine references TIR <0.015. Final grind the sprayed journals to size and tolerance.Operator to do in -process inspections 0.2mm from final size. Final grind to obtain surface finish of Ra 0.1-0.2. Ensure no chatter or spiral after final grind. Coated Area to be sealed with anaerobic sealer after finishing. Complete and sign all required paperwork
NDT |  | Dye penetrant test Linear shaft main body with water washable Ardrox 907PB dye penetrant Allow to stand for 30 mins minimum and wipe all excess dye with soft paper towel or cloth Apply Ardrox 9D1B developer. Any relevant indications to be reported to Supervisor immediately before removing developer from hydraulic rod
Sealing |  | Using dicthol sealer
Engraving |  | ENGRAVE JOB NUMBER ON PART
Finishing |  | Remove all masks De-burr all overspray. Break sharp edges.
Minimum process validation |  | Visually inspect to ensure there are no coating defects (pinholes, cracks, discoloration, uneven roughness, edge delamination). Perform complete dimensional check as per inspection report and record.
Release for delivery |  | Final inspection by responsible Foreman
QCP approval | [7 empty] | * Customer QC requirements
For Surcotec |  |  | For Customer |  |  |  |  | H | Hold point (verification by customer is mandatory)
Name: |  |  | Name: |  |  |  |  | W | Witness point (verification by customer is discretrionary)
[8 empty] | I | Inspection point (verification by customer is discretrionary)
Signature: |  |  | Signature:
Date: |  |  | Date:
Surcotec Confidential
ISO 9001:2015 Quality Management System

## PI
Surcotec
ST-F-09-01-8111 - Rev1 - Atlantis Foundries - 160Ø Linear Shafts for HVOF Coating
Revision:1
Pre-inspection
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Tolerance | 0° | 120° | 240° | Length | Run-out | Ra | Notes
Pre-Inspection Linear Shaft 1
1
2
3
Pre-Inspection Linear Shaft 2
1
2
3
Intermediate Inspection Linear Shaft 1
1
2
3
Intermediate Inspection Linear Shaft 2
1
2
3
Micrometer |  | Vernier |  | Serial Number |  |  | Size

## Machining notes
Surcotec
ST-F-09-01-8111 - Rev1 - Atlantis Foundries - 160Ø Linear Shafts for HVOF Coating
Revision:1
Machining notes
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Prep size | Reference | Run-out | Squareness reference | Squareness run-out | Notes
Linear Shaft.1
1 | Linear Shaft
Intermediate Linear Shaft.1
2 | Linear Shaft
Linear Shaft.2
1 | Linear Shaft
Intermediate Linear Shaft.2
2 | Linear Shaft
Micrometer |  | Vernier |  | Serial Number |  |  | Size

## Spray notes
Surcotec
ST-F-09-01-8111 - Rev1 - Atlantis Foundries - 160Ø Linear Shafts for HVOF Coating
Revision:1
Spray Notes/Belzona Notes
|  |  |  | System | Material Used | Code | Qty Out | Qty In | Qty Used
[7 empty] | kg | kg | kg
Material Batch/Lot# |  |  |  | Arc System | ARC Top Coat | 1302 ( 10T ) | kg | kg | kg
Material Batch/Lot# | [6 empty] | kg | kg | kg
Material Batch/Lot# |  |  |  | HVOF System | HVOF Powder | 3604 (1275 HGB) | kg | kg | kg
Time start |  |  | Time Finish |  |  |  | kg | kg | kg
Nr | Description | Prep size | Final size | Cycles | As-spray size | Notes
Intermediate Coating Linear Shaft.1 | [6 empty] | Spray Size
1
Intermediate Coating Linear Shaft.2 | [6 empty] | Spray Size
2
HVOF Coating Linear Shaft.1 | [6 empty] | Spray Size
1
HVOF Coating Linear Shaft.2 | [6 empty] | Spray Size
2
| Date: |  |  | Name: |  |  | Sign:
Surcotec
0
20.01.2026
Spray Notes/Belzona Notes
[5 empty] | Material Used | Code | Qty Out | Qty In | Qty Used
[7 empty] | kg | kg | kg
| System |  |  |  | ARC Top Coat | 1302 ( 10T ) | kg | kg | kg
| Material Type | [5 empty] | kg | kg | kg
| Material lot# |  |  |  | HVOF Powder | 3604 (1275HGB) | kg | kg | kg
| Time start |  | Time Finish |  |  |  | kg | kg | kg
Nr | Description | Prep size | Final size | Cycles | As-spray size | Notes
Intermediate Coating Linear Shaft.2 | [6 empty] | Spray Size
1 | Main Piston Body
HVOF Coating Linear Shaft.2 | [6 empty] | Spray Size
2 | Main Piston Body
| Date: |  |  | Name: |  |  | Sign:

## FI
Surcotec
ST-F-09-01-8111 - Rev1 - Atlantis Foundries - 160Ø Linear Shafts for HVOF Coating
Revision:1
Final inspection
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Tolerance | 0° | 120° | 240° | Run-out | Ra | Sign Artisan | Sign Inspector
Final Inspection Linear Shaft 1
1
2
3
4
Final-Inspection Linear Shaft 2
1
2
3
4
Micrometer |  | Vernier |  | Serial Number |  |  | Size

## Sheet1
Job log sheet
Part |  | 160 Ø Linear Shaft for HVOF Coating |  | Date received | 20.01.2026 | Responsible person | Ian Walsh
Job Number |  | IOB 22941 |  | Date required | 10-15 Days | Captured by | Ilhaam Klein
Customer |  | Atlantis Foundries |  | Date delivered |  | Date | 20.01.2026
Quantity |  | 2-off |  | Linear Shaft 2
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
1. Pre-machining/Rough machining
- Load
- Set-up
- Machine
2. Pre-machining after Heat Treatment
- QC Foreman/Supervisor
- Remove
2. Spray ARC Intermediate Coating
- Pre-Heat/Mask
- Blast
- Load
- Set-up
- Arc Spray Intermediate Coating
- QC Foreman/Supervisor
- Remove
3. Machining (Intermediate Coating for HVOF)
- Load (Include machine prep for job)
- Set-up
- Machine (Including de-burring & detailing)
- QC Foreman/Supervisor
- Remove
4. Spray HVOF Top Coat
- Pre-Heat/Mask
- Blast
- Load
- Set-up
- Coat HVOF
- Cool Down
- Coat HVOF
- Cool Down
- Coat HVOF
- Cool down
- QC Foreman/Supervisor
- Remove
IOB 22941 Atlantis -Linear Shafts Page 2
5. Final Grinding & Polishing
- Load
- Set-up
- Grinding
- Final Polishing
- QC Foreman/Supervisor & Remove
- Remove
Other
IOB 17367 Hytec Hydraulic Rod Page 2
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
3. Intermediate Machining
- Load
- Set-up
- Machine
2. Pre-machining after Heat Treatment
- QC Foreman/Supervisor
- Remove
2. Spray ARC Intermediate Coating
- Pre-Heat/Mask
- Blast
- Load
- Set-up
- Arc Spray Intermediate Coating
-
- QC Foreman/Supervisor
- Remove
Other
Other (e.g. Welding, painting etc.)
Date | Employee |  | Details |  |  | Start | End | Total
Machine/Booth running time
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total

## Sheet2
PO # | Atlantis Foundries |  |  | IOB: 22941
ST-F-09-01-8111 |  |  |  | Quote SCT - 7725
Ref # 26-01-027
160 Ø Linear Shafts for HVOF Coating (2-off)
Description:
Reference: | Ian Walsh
NOTES:
ORDER NUMBER
| JOB CARD (COMPLETED) |  | DELIVERY NOTE #
DELIVERY NOTE
COSTING BREAKDOWN
INVOICED
Costing Approved by: |  | Date: