## Front page
Surcotec
ST-F-09-01-8189-Rev 1-Petec Services-STB Winch Repairs Donna Jane(3-Off Parts)
Revision:1
Cover Page
Job Number
IOB 23019
Part Description
STB Winch Repairs Donna Jane
Number of parts : | 3-Off Parts
Responsible person : | Ian Walsh
Customer : | Petec Services
Customer job number:
Customer ref. number: | Donna Jane
Quote number: | SCT -
Surcotec Ref. Number: | 26-02-056
Customer order number:
Customer Drawing number(s) : | N/A
Date created: | 27.02.2026
Due date: | 06.03.2026
Delivery note(s):
NOTE(S)
ISO 9001:2015
Surcotec Confidential

## Quality control plan
Surcotec
ST-F-09-01-8189-Rev 1-Petec Services-STB Winch Repairs Donna Jane(3-Off Parts)
Revision:1
Quality controll plan
Purpose: Prepared by responsible engineer to describe the actual work to be done. Defines customer QC requirements.
Job number: | IOB 23019 |  | Description: | STB Winch Repairs Donna Jane |  | QC Clearance |  |  |  | Total time | Comments
Revision: | 3-Off Parts |  | Quantity: | 3-Off Parts |  | Surcotec |  | Subcontractor
Operation |  | Description |  |  |  | Name | Date | Name | Date
Register job and Issue WDP document |  | Register job
Incoming inspection |  | Visual, dimensional & geometrical inspection. Record all pertinent dimensions, tolerences & sizes. Create drawing/sketch if none was provided by client. Record all findings on pre-inspection report & submit to (BG)
Pre-machining |  | Set-up Line Boring Equipment Clock to the Bore and face and set bars parrallel to one another, TIR<0.015mm (TIR include all journals and roll bodies if applicable) Pre-machine the indicated Bores to remove damage and/or old coating, pre-machine size must be minimum 1.0mm bigger than the final size on diameter. Ensure radii in all corners. Complete all required paperwork & sign.
Welding |  | Weld up frame bores using compatable welding consumables. Please follow all relevant preperations and welding procedures. Please ensure part will clean up during final machining without any welding defects. Complete all relevant paperwork and sign.
NDT |  | Dye penetrant test with water washable Ardrox 907PB dye penetrant Allow to dry for 30 mins minimum Apply Ardrox 9D1B developer | [8 empty] | HOLDING POINT (3RD Party NDT)
Centres |  | Centres between Top Bore and Middle Bore 200 OEM.
Pre-machining |  | Set-up Line Boring Equipment and set bars parrallel to each other. Clock to the Bore and face, TIR<0.015mm (TIR include all journals and roll bodies if applicable) Pre-machine the indicated Bores to remove damage and/or old coating, pre-machine size must be minimum 1.0mm bigger than the final size on diameter. Ensure radii in all corners. Complete all required paperwork & sign.
Skim Bores |  | Set-up Line Boring Equipment and set bars parrallel to each other. Clock to the bores and ensure the centre to centre distances are correct.TIR<0.015mm (TIR include all journals and roll bodies if applicable) Skim bore to size and tolerance as per drawing supplied by customer.(Ø125 +0.02 / -0.00) Ensure radii in all corners. Complete all required paperwork & sign.
In Process Inspection |  | Artisan to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
Centres |  | Centres between Middle Bore and Bottom Bore 730 OEM.
Pre-machining Winch Drum |  | Set-up on the Lathe. Clock to the Spigot and face, TIR<0.015mm (TIR include all journals and roll bodies if applicable) Pre-machine the indicated Bearing journal on stub end to remove damage and/or old coating, pre-machine size must be minimum 0,5mm bigger than the final size on diameter. Ensure radii in all corners. Complete all required paperwork & sign.
In Process Inspection |  | Artisan to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
NDT |  | Dye penetrant test with water washable Ardrox 907PB dye penetrant Allow to dry for 30 mins minimum Apply Ardrox 9D1B developer
Welding |  | Weld up frame bores using compatable welding consumables. Please follow all relevant preperations and welding procedures. Please ensure part will clean up during final machining without any welding defects. Complete all relevant paperwork and sign.
Thermal spray Bond coat on Stub |  | Spray 1001 Mix (75B) top coat on Pre-machined bearing journals. Spray 1.2mm over final size on diameter for grinding/machining allowances Complete all required paperwork & sign.
Thermal spray topcoat on Stub |  | Spray 1201 Mix (60T) top coat on Pre-machined bearing journal. Spray 1.2mm over final size on diameter for grinding/machining allowances Complete all required paperwork & sign.
Thermal spray Bond coat in Gearbox |  | Spray 1001 Mix (75B) top coat on Pre-machined bearing journal. Spray 1.2mm over final size on diameter for grinding/machining allowances Complete all required paperwork & sign.
Thermal spray topcoat in Gearbox |  | Spray 1201 Mix (60T) top coat on Pre-machined bearing journal. Spray 1.2mm over final size on diameter for grinding/machining allowances Complete all required paperwork & sign.
Final-machining Winch Drum Stub and Brake band |  | Set-up on the Lathe. Clock to the Spigot and face, TIR<0.015mm (TIR include all journals and roll bodies if applicable) Skim Brake band and Face till true and clean. Final-machine the indicated Bearing journal on stub end to Ø90.00 +0.035 remove damage and/or old coating, pre-machine size must be minimum 0,5mm bigger than the final size on diameter. Ensure radii in all corners. Complete all required paperwork & sign.
Final-machining Winch Drum Face |  | Turn Winch Drum and Set-up on the Lathe. Clock to the Brake band and face on stub end and clock spigot on opposite end true over 4 Jaws, TIR<0.015mm (TIR include all journals and roll bodies if applicable) Final-machine indicated face till clean and true. Ensure radii in all corners. Complete all required paperwork & sign.
In Process Inspection |  | Spray Technician to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
Final-machining Top Bores |  | Set-up Line boring Equipment and clock to Pre-machining references. Ensure TIR<0.015mm. Final machine to specified dimensions and tolerance as per drawing supplied by customer Ø130 H7 +0.035 / -0.00 Ensure no spiral or chatter on surface. Ensure a surface roughness off Ra=0,15-0,35. Re-machine any radii or undercuts. Complete all required paperwork & sign.
Detail Machining |  | Set-up in the lathe. Clock to the bearing journals, TIR<0.015mm (TIR include all journals and roll bodies if applicable) Machine to clean all undercuts do detailing as per original detailing. Ensure radii in all corners. Complete all required paperwork & sign. | [8 empty] | Per Part
Final-machining/grinding on Rotor Bearing Journals |  | Set-up on Lathe and clock to Pre-machining references. Ensure TIR<0.015mm. Final machine/grind the sprayed Bearing Journals to size and tolerance as per customer. Ensure no spiral or chatter on surface. Ensure a surface roughness off Ra=0,15-0,35. Re-machine any radii or undercuts. Complete all required paperwork & sign.
Final-machining Bottom Bores |  | Set-up Line boring Equipment and clock to Pre-machining references. Ensure TIR<0.015mm. Final machine to specified dimensions and tolerance as per drawing supplied by customer Ø160 +0.02 / -0.00 - Ø343.80 +0.02 / -0.00 Ensure no spiral or chatter on surface. Ensure a surface roughness off Ra=0,15-0,35. Re-machine any radii or undercuts. Complete all required paperwork & sign.
Finishing |  | Remove all masks De-burr all overspray. Break sharp edges.
Minimum process validation |  | Visually inspect to ensure there are no coating defects (pinholes, cracks, discoloration, uneven roughness, edge delamination). Perform complete dimensional check as per inspection report and record.
Release for delivery |  | Final inspection by responsible Foreman
QCP approval | [7 empty] | * Customer QC requirements
For Surcotec |  |  |  |  | For Customer |  |  | H | Hold point (verification by customer is mandatory)
Name: |  |  |  |  | Name: |  |  | W | Witness point (verification by customer is discretrionary)
[8 empty] | I | Inspection point (verification by customer is discretrionary)
Signature: |  |  |  |  | Signature:
Date: |  |  |  |  | Date:
Surcotec Confidential

## PI
Surcotec
ST-F-09-01-8189-Rev 1-Petec Services-STB Winch Repairs Donna Jane(3-Off Parts)
Revision:1
Pre/Final-inspection
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Tolerance | 0° | 120° | 240° | Length | Run-out | Ra | Notes
Winch Drum Pre Inspection
1
2
3
4
5
6
Winch Drum Final Inspection
1
2
3
4
5
6
Micrometer |  | Vernier |  | Serial Number |  |  | Size

## Spray and Machine
Surcotec
ST-F-09-01- 8189-Rev 1-Petec Services-STB Winch Repairs Donna Jane(3-Off Parts)
Spray Notes/Belzona Notes
Nr | Description | Prep size |  | Final size |  | Notes
Machining Notes
1 | Gearbox Bore
2 | Gearbox Bore
3 | Gearbox Bore
1 | Stub Bearing
| Material | Code | KG out | KG in | Used
| Welding | Mig Wire
| ARC Bond Coat | 1001(75B)
| ARC Top Coat | 1201(60T)
Spray Notes
Nr | Description | Prep size | Final size | Cycles | As-spray size | Spray Size
1 | Gearbox Bore
2 | Gearbox Bore
3 | Gearbox Bore
1 | Stub Bearing
Welding - Frame
1 | Top Bore
2 | Top Bore
1 | Bottom Bore
2 | Bottom Bore
Date: |  |  |  | Name & Sign

## Machining notes
Surcotec
ST-F-09-01-8189-Rev 1-Petec Services-STB Winch Repairs Donna Jane(3-Off Parts)
Revision:1
Machining notes
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Prep size | Reference | Run-out | Squareness reference | Squareness run-out | Notes
Bearing Housing Bore
1 | Bore
1 | Bearing Journal
2 | Bearing Journal
Illustration

## Spray notes
Surcotec
ST-F-09-01-8189-Rev 1-Petec Services-STB Winch Repairs Donna Jane(3-Off Parts)
Revision:1
Spray Notes/Belzona Notes
[5 empty] | Material Used | Code | Qty Out | Qty In | Qty Used
| System | Bearing Housing Bore |  |  | ARC Bond Coat | 1001 ( 75 B ) | kg | kg | kg
| Material Type |  |  |  | ARC Top Coat | 1600 (ALCRO) | kg | kg | kg
| Material lot# |  |  |  | ARC Bond Coat | 1001 ( 75 B ) | kg | kg | kg
[5 empty] | ARC Top Coat | 1600 (ALCRO) | kg | kg | kg
Nr | Description | Prep size | Final size | Cycles | As-spray size | Notes | Spray Size
Bearing Block
1 | Bearing Housing Bore
1
2
| Date: |  |  | Name: |  |  | Sign:

## FI
Surcotec
ST-F-09-01-8189-Rev 1-Petec Services-STB Winch Repairs Donna Jane(3-Off Parts)
Revision:1
Pre-Final inspection
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Tolerance | 0° | 120° | 240° | Run-out | Ra | Sign Artisan | Sign Inspector
Pre-Inspection - Gearbox
1
2
3
Pre-Inspection - Frame
1 | Top Bore
Pre-Inspection Rotor
1 | Drive Journal
2 | Bearing
3 | Seal
4 | Body
5 | Seal
6 | Bearing
2 | Top Bore
3 | Middle Bore
4 | Middle Bore
5 | Bottom Bore
6 | Bottom Bore
Final-Inspection - Gearbox
1
2
3
Final-Inspection - Frame
1 | Top Bore
Final-Inspection Rotor
1 | Drive Journal
2 | Bearing
3 | Seal
4 | Body
5 | Seal
6 | Bearing
2 | Top Bore
3 | Middle Bore
4 | Middle Bore
5 | Bottom Bore
6 | Bottom Bore
Micrometer |  | Vernier |  | Serial Number |  |  | Size

## Sheet1
Job log sheet
Part |  | Winch Frame and Gearbox Repair |  | Date received | 13.02.2026 | Responsible person | Ian Walsh
Job Number |  | IOB 22980 |  | Date required | ASAP | Captured by | Oscar February
Customer |  | Petec Services |  | Date delivered |  | Date | 13.02.2026
Quantity |  | 2-Parts
Machine/Booth running time
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
1. Pre-Machining Winch Drum
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Stub Bearing
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Bore 2
- QC (Foreman etc)
- Remove from Machine
2. Pre-Machining
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machine
- QC (Foreman etc)
- Remove from Machine
1. Pre-Machining Winch Frame Top
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Bore
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Bore 2
- QC (Foreman etc)
- Remove from Machine
2. Machining Winch Frame Middle
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Bore
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Bore 2
- QC (Foreman etc)
- Remove from Machine
3. Pre-Machining Winch Frame Bottom
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Bore
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Pre- Machine - Bore 2
- QC (Foreman etc)
- Remove from Machine
4. Welding
- Weld
- Pre-Heat/Mask - Bore 2
- Blast
- Load & Setup
- Coat (Start to finish, include cool down time(s)
- QC Foreman/Supervisor
- Remove from booth
5. Welding
- Weld
- Pre-Heat/Mask - Bore 2
- Blast
- Load & Setup
- Coat (Start to finish, include cool down time(s)
- QC Foreman/Supervisor
- Remove from booth
6. Final-Machining Winch Frame Top
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Bore
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Bore 2
- Detail Machining/Polishing
7. Final-Machining Winch Frame Bottom
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Bore
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Bore 2
- Detail Machining/Polishing
8. Final-Machining Winch Drum
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Stub Bearing Journal
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Bore 2
- Detail Machining Brake Band and Face
8. Final-Machining Winch Drum
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Skim Face
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Final Machining - Bore 2
- Detail Machining/Polishing
9.Other
IOB 16768 Basticks-Hasegawa Crankshafts Page 2
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
1. Spray Crankshaft 4
- Pre-Heat/Mask
- Blast
- Load
- Set-up (Including masking)
- Coat (Start to finish, include cool down time(s)
- Coat (Start to finish, include cool down time(s)
- QC Foreman/Supervisor
- Remove from booth
1. Spray Crankshaft 5
- Pre-Heat/Mask
- Blast
- Load
- Set-up (Including masking)
- Coat (Start to finish, include cool down time(s)
- Coat (Start to finish, include cool down time(s)
- QC Foreman/Supervisor
- Remove from booth
1. Spray Crankshaft 6
- Pre-Heat/Mask
- Blast
- Load
- Set-up (Including masking)
- Coat (Start to finish, include cool down time(s)
- Coat (Start to finish, include cool down time(s)
- QC Foreman/Supervisor
- Remove from booth
IOB 16768 Basticks-Hasegawa Crankshafts Page 3
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
1. Spray Crankshaft 7
- Pre-Heat/Mask
- Blast
- Load
- Set-up (Including masking)
- Coat (Start to finish, include cool down time(s)
- Coat (Start to finish, include cool down time(s)
- QC Foreman/Supervisor
- Remove from booth
Other (NDT, Sealing etc)
1. Spray Crankshaft 8
- Pre-Heat/Mask
- Blast
- Load
- Set-up (Including masking)
- Coat (Start to finish, include cool down time(s)
- Coat (Start to finish, include cool down time(s)
- QC Foreman/Supervisor
- Remove from booth

## Sheet2
PO # | Petec Services |  | IOB: 23019
ST-F-09-01-8189 |  |  | Quote: SCT -
Ref # 26-02-056
STB Winch Repairs Donna Jane(3-Off Parts)
Description:
Reference: | Ian Walsh
NOTES:
ORDER NUMBER
| JOB CARD (COMPLETED) |  | DELIVERY NOTE #
DELIVERY NOTE
COSTING BREAKDOWN
INVOICED
Costing Approved by: |  | Date: