## Front page
Surcotec
ST-F-09-01-8224-Rev 1-CTP Printers - Roller Bearing Bore Repair
Revision:1
Cover Page
Job Number
IOB 23054
Part Description
Roller Bearing Bore Repair
Number of parts : | 1-Off
Responsible person : | Ian Walsh
Customer : | CTP Printers
Customer job number: | N/A
Customer ref. number: | N/A
Quote number: | SCT - 7843
Surcotec Ref. Number: | 26-03-035
Customer order number:
Customer Drawing number: | N/A
Date created: | 11.03.2026
Due date: | 16.03.2026
Delivery note(s):
NOTE(S)
ISO 9001:2015
Surcotec Confidential

## Quality control plan
Surcotec
ST-F-09-01-8224-Rev 1-CTP Printers - Roller Bearing Bore Repair
Revision:1
Quality controll plan
Purpose: Prepared by responsible engineer to describe the actual work to be done. Defines customer QC requirements.
Job number: | IOB 23054 |  | Description: | Roller Bearing Bore Repair |  | QC Clearance |  |  |  | Total time | Comments
Revision: | 1-Off |  | Quantity: | 1-Off |  | Surcotec |  | Subcontractor
Operation |  | Description |  |  |  | Name | Date | Name | Date
Register job and Issue WDP document |  | Register job
Incoming inspection |  | Visual, dimensional & geometrical inspection. Record all pertinent dimensions, tolerences & sizes. Create drawing/sketch if none was provided by client. Record all findings on pre-inspection report & submit to (BG)
Pre-machining |  | Set-up Shaft in the lathe. Clock to bore and face . TIR<0.02mm (TIR include all journals if applicable) Pre-machine 1 x Bearing Bore to remove damage and/or old coating, pre-machine size must be minimum 0,5mm under the final size on diameter. Coppersulfhate to be used on machined journals, chamfers and leading edges as to ensure all old coating removed.Operator to clean part with acetone after pre-machining. Ensure radii in all corners. Complete all required paperwork & sign.
Pre-grinding
Welding |  | Press a pin into hole on shaft and weld to close up using compatable welding consumables. Fettle welding if necessary
Milling & Drilling |  | Set up shaft on Milling Machine. Drill a new hole to suit the pin provided by the customer. Pin to line up with mating part provided and to be a tight fit. Please ''measure twice and cut once''. Complete and sign required paperwork
In Process Inspection |  | Artisan to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
In process inspection
NDT |  | Dye penetrant test pre-machined journals with water washable Ardrox 907PB dye penetrant Allow to dry for 30 mins minimum Apply Ardrox 9D1B developer. Supervisor to be informed of any visual indications. | [8 empty] | Hold & witness point
Specialised subcontracting
Welding before coating
Preperation for pre heating and sand blast |  | Pre-heat part. Wash with acetone and repeat process until no indication of contimaminents visible.
Gritblasting |  | Grit blast using GH18 Chilled Iron grit. Gritblasting to be done until the area to be coated exhibits a uniform structure to Sa2½ standard. After gritblasting clean dust by blasting with clean dry compressed air, and check for trapped grit and residue.
In Process Inspection |  | QC Specialist, Forman or Superintendant to perform in process checking for blasting profile using the Elcometer and record all findings. | [8 empty] | HOLDING POINT
Masking for coating |  | Use specialised tape or anti bond paint to mask non-spray areas.
Thermal spray Bond coat |  | Spray 0,2mm on diameter 1001 bond-coat or, if the pre-machine size is higher than 2mm on diameter to within 1mm from final size. Top coat to be sprayed directly on as-sprayed bond-coat.
Thermal spray topcoat |  | Spray 1600 (Alcro) top-coat on pre machined journal Spray 1.0mm oversize on diameter for grinding/machining allowance. Complete all required paperwork & sign.
Welding
Proof machining of welding
NDT of welding after proof machining
Heat-treatment of welding after proof machining
Final-machining |  | Set-up in the Lathe and clock to Pre machining references. Ensure TIR<0.015mm. Final machine the sprayed journal to size and tolerance (DP to advise) Ensure no spiral or chatter on surface. Ensure a surface roughness off Ra=0,15-0,35. Re-machine any radii or undercuts. Complete all required paperwork & sign.
In Process Inspection |  | Spray Technician to perform dimensional and geometrical inspection. QC Specialist, Forman or Superintendant to perform in process checking and record all findings. | [8 empty] | HOLDING POINT
Final-Machining |  | Set-up and clock to pre-machining references. Ensure TIR<0.015mm. Final Machine the sprayed Bore to original recorded dimensions (OF to advice). Ensure no spiral or chatter on surface.Operator to do in-process inspections 0.2mm from final size.Shop foreman /supervisor to witness and sign. Ensure a surface roughness off Ra=0,15-0,35. Complete all required paperwork & sign.
NDT |  | Dye penetrant test Final-machined journal with water washable Ardrox 907PB dye penetrant Allow to dry for 30 mins minimum Apply Ardrox 9D1B developer. Supervisor to be informed of any visual indications. | [8 empty] | Hold & witness point
Engraving |  | ENGRAVE JOB NUMBER ON PART
Finishing |  | Remove all masks De-burr all overspray. Break sharp edges.
Sealing of coating |  | Seal with Dichtol sealer.
NDT of welding after completion of work |  | Dye penetrant test shaft with water washable Ardrox 907PB dye penetrant Allow to dry for 30 mins minimum Apply Ardrox 9D1B developer
Minimum process validation |  | Visually inspect to ensure there are no coating defects (pinholes, cracks, discoloration, uneven roughness, edge delamination). Perform complete dimensional check as per inspection report and record.
Special process validation
Specialised subcontracting
Release for delivery |  | Final inspection by responsible Foreman
QCP approval
For Surcotec |  |  |  | For Customer
Name: |  |  |  | Name:
Signature: |  |  |  | Signature:
Date: |  |  |  | Date:
Surcotec Confidential

## PI
Surcotec
ST-F-09-01-8224-Rev 1-CTP Printers - Roller Bearing Bore Repair
Revision:1
Pre-inspection
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Tolerance | 0° | 120° | 240° | Length | Run-out | Ra | Notes
Pre Inspection
1
2
3
4
Pre Inspection Shaft 2
1
2
3
4
Pre Inspection Shaft 3
1
2
3
4

## Spray and Machine
Surcotec
ST-F-09-01-8224 -Rev 1-CTP Printers - Roller Bearing Bore Repair
Spray Notes/Belzona Notes
Nr | Description | Prep size |  | Final size |  | Notes
Machining Notes
1
2
3
4
5
6
7
8
System |  | Material Batch /Lot | Material | Code | KG Out | KG In | KG Used
Arc System |  |  | Bond Coat | 1001 (75B)
Arc System |  |  | Top Coat | 1600 (Alcro)
Arc System |  |  | Bond Coat | 1001 (75B)
Arc System |  |  | Top Coat | 1600 (Alcro)
Spray Notes
Nr | Description | Prep size | Final size | Cycles | As-spray size | Spray Size
1
2
3
4
5
Date: |  |  |  | Name & Sign

## Log sheet
Job log sheet
Part |  | Roller bearing Bore Repair |  | Date received | 11.03.2026 | Responsible person | Ian Walsh
Job Number |  | IOB 23054 |  | Date required | 16.03.2026 | Captured by | Oscar February
Customer |  | CTP Printers |  | Date delivered |  | Date | 11.03.2026
Quantity |  | 1-Off
Machine/Booth running time
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
`
1. Pre-machining
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Machine / grind
- QC Foreman/Supervisor
- Remove
- Load (Including machine prep for job) SHAFT .2
- Set-up (Including QCP review)
- Machine / grind
- QC Foreman/Supervisor
- Remove
- Load (Including machine prep for job) SHAFT .3
- Set-up (Including QCP review)
- Machine / grind
- QC Foreman/Supervisor
- Remove
2. Spray (2)
- Pre-Heat/Mask
- Blast
- Load /Set-up (Including masking)
- ARC Spray Coat
- QC Foreman/Supervisor
- Pre-Heat/Mask SHAFT.2
- Blast
- Load /Set-up (Including masking)
- ARC Spray Coat
- QC Foreman/Supervisor
IOB 17734 Petec Services Scroll Shafts Page 2
- Pre-Heat/Mask SHAFT.3
- Blast
- Load /Set-up (Including masking)
- ARC Spray Coat
- QC Foreman/Supervisor
- Remove
3. Milling Machine
- Load (Including machine prep for job)
- Set-up (Including QCP review)
- Machine / grind
- QC Foreman/Supervisor
- Remove
3. Final Machining
- Load (Include machine prep for job)
- Set-up
- Machine / grind
- QC Foreman/Supervisor
- Remove
IOB 17862 Petec Services Control Shafts Page 2
- Load (Include machine prep for job) SHAFT.2
- Set-up
- Machine / grind (Include wheel dressing)
- QC Foreman/Supervisor
- Remove
- Load (Include machine prep for job) SHAFT.3
- Set-up
- Machine / grind (Include wheel dressing)
- QC Foreman/Supervisor
- Remove
Other (NDT,Welding,Sealant etc)
IOB 16805 Chevron - 69G-100C Shaft Page 2
Machine/Booth running time
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
`
5. Spray (2)
- Pre-Heat/Mask
- Blast
- Load
- Set-up (Including masking, programming)
- HVOF Coat
- Cool Down
- HVOF Coat
- Cool Down
- HVOF Coat
- Cool Down
- HVOF Coat
- Cool Down
- QC Foreman/Supervisor
- Remove
Inspection
Date | Inspector |  | Inspection Details |  |  | Start | End | Total
Other (e.g. Welding, painting etc.)
Date | Employee |  | Details |  |  | Start | End | Total
Job log sheet
Part |  | VTR 400/401 Rotor |  | Date received | 11.03.2026 | Responsible person | Ian Walsh
Job Number |  | IOB 23054 |  | Date required | 16.03.2026 | Captured by
Customer |  | CTP Printers |  | Date delivered | 0 | Date
Quantity |  | 0
Machine/Booth running time
Date | Artisan | Machine | Description of activity |  |  | Work start | Work end | Total
5. Spray (2)
- Pre-Heat/Mask
- Blast
- Load
- Set-up (Including masking, programming)
- HVOF Coat
- Cool Down
- HVOF Coat
- Cool Down
- HVOF Coat
- Cool Down
- HVOF Coat
- Cool Down
- QC Foreman/Supervisor
- Remove
3. Machining / polishing / grinding (1) Shaft 2
- Load (Include machine prep for job)
- Set-up
- Machine / grind (Include wheel dressing)
- QC Foreman
- Remove

## FI
Surcotec
ST-F-09-01-8224-Rev 1-CTP Printers - Roller Bearing Bore Repair
Revision:1
Pre/Final inspection
| Date |  |  |  |  | Time start
| Machine |  |  |  |  | Time finish
Artisan
Nr | Description | Tolerance | 0° | 120° | 240° | Run-out | Ra | Sign Artisan | Sign Inspector
Pre-Inspection
1
2
3
6
7
8
Final-Inspection
1
2
3
6
7
8
Micrometer |  | Vernier |  | Serial Number |  |  | Size

## Cover Page
PO# | CTP Printers |  | IOB 23054
ST-F-09-01-8224 |  |  | Quote Ref : SCT - 7843
Ref # 26-03-035
Roller Bearing Bore Repair (1-off)
Description:
Reference: | Ian Walsh
NOTES:
ORDER NUMBER
| JOB CARD (COMPLETED) |  | DELIVERY NOTE #
DELIVERY NOTE
COSTING BREAKDOWN
INVOICED
Costing Approved by: |  | Date: